DAY-BY-DAY EXECUTION PLAN

Companion to: Isolating Tokenization Fertility from the Mean-Pooling Confound (Urdu–Hindi / Serbian Cyrillic–Latin)

Window: July 19 – August 25, 2026 (38 days) · Buffer: August 26–30, 2026

# How to Read This Plan

This expands Section 12 of the proposal into the day-by-day task assignments referenced there. It is organized into five weeks, each closing on a hard checkpoint (Section 12: work does not proceed past a checkpoint that has not cleared). Method A must clear its pass / proceed-with-discrepancy / stop gate before Method B begins in earnest — some Method B prep (tokenizer sampling verification) can run in parallel since it does not depend on Method A's outcome.

Immediate action (before Day 1 tasks resume) Rewrite the sentence in Section 6 flagged as lifted verbatim from the COLING 2025 source. Do this first — it blocks nothing else, but it's a standing liability the longer it sits in the draft.

# Week 1 — Setup, Pre-Registration, Method A Launch

Day 1 — Jul 19 (Sun)   Kickoff

- Stand up the repo skeleton (code, data, results, preregistration folders).

- Pull FLORES-200; verify Urdu/Hindi and Serbian Cyrillic/Latin split sizes and coverage directly against the dataset (do not assume from the dataset card).

- Fork Del & Fishel's xsim codebase; get it importable in your environment.

Day 2 — Jul 20 (Mon)   Environment + lit-review closeout

- Finish the COLING-2025 rewrite from the flagged sentence above; re-read surrounding paragraph for any other close paraphrase.

- Resolve environment/dependency issues for xsim (mBERT/XLM-R weights, tokenizer versions pinned).

- Draft the OSF pre-registration skeleton: hypotheses (RQ1–RQ4), primary analysis plan, TOST smallest-effect-size-of-interest.

Day 3 — Jul 21 (Tue)   Smoke test

- Run the forked xsim pipeline end-to-end on a trivial toy input — confirm it runs before trusting any real number.

- Fix any broken plumbing surfaced by the smoke test.

Day 4 — Jul 22 (Wed)   Method A reproduction — pass 1

- Reproduce Del & Fishel's published Urdu/Hindi/Swahili/Thai CKA-outlier clustering.

- Log any deviation from published numbers immediately rather than at the end of the week.

Day 5 — Jul 23 (Thu)   Method A reproduction — pass 2

- Extend the reproduction to cosine similarity and nearest-neighbor accuracy, identically across layers and models.

- Compute Serbian-Cyrillic×Serbian-Latin equivalents to the Urdu×Hindi numbers.

Day 6 — Jul 24 (Fri)   Token-level CKA + ANC

- Implement token-level, position-aligned CKA (no pooling step) alongside the standard pooled CKA.

- Read Del & Fishel (2022) on ANC; implement ANC as the third similarity index.

Day 7 — Jul 25 (Sat)   Checkpoint 1

- Freeze Method A's raw outputs: pooled CKA, token-level CKA, cosine, ANC, NN-accuracy for both pairs.

- Write up the reconciliation finding in plain terms: does the reproduction resolve the Pires vs. Del & Fishel disagreement, and does token-level CKA show the length/fertility sensitivity Mitra & Kumar (2026) predict?

Checkpoint 1 gate (end of Day 7) Apply the pass / proceed-with-discrepancy / stop rule to the Method A reproduction. A clean pass moves straight into Week 2. A discrepancy that's explainable (e.g. version drift, metric definition) can proceed with the discrepancy documented. An unexplained failure to reproduce means stop — do not carry an unresolved reproduction into Method B.

# Week 2 — Method A Close-Out, Method B Prep

Day 8 — Jul 26 (Sun)   Method A write-up

- Finalize the Method A section of the paper (or working draft) with all four metrics reported side by side for both language pairs.

Day 9 — Jul 27 (Mon)   Serbian-pair depth decision

- Using remaining project runway as of Checkpoint 1, decide: does the Serbian pair get the full statistical treatment, or is it reported as a lighter preliminary robustness check?

- Document the decision and reasoning — this is one of the pre-committed contingency points from Section 12.

Day 10 — Jul 28 (Tue)   XLM-R sampling verification

- Enable SentencePiece's sampling mode (BPE-dropout, alpha) on the XLM-R tokenizer.

- Manually inspect sampled segmentations on real Urdu, Hindi, and Serbian words — confirm behavior matches documentation before trusting it at scale.

Day 11 — Jul 29 (Wed)   mBERT sampling setup

- Get Hiraoka's MaxMatch-Dropout implementation running against mBERT's WordPiece vocabulary file.

- Budget real adaptation time here — treat it as a smaller research codebase, not a drop-in library.

Day 12 — Jul 30 (Thu)   Sampling-bias feasibility check

- Time-boxed feasibility check: can Cognetta et al.'s uniform-sampling (FST lattice) algorithm be implemented for both tokenizers in the time remaining?

- If yes: begin implementation. If no: draft the explicit limitation language for the asymmetric sampling-bias fallback.

Day 13 — Jul 31 (Fri)   Pre-registration finalize

- Finalize and timestamp the OSF pre-registration (hypotheses, primary analysis plan, TOST threshold) before any Method B result exists.

Day 14 — Aug 1 (Sat)   Checkpoint 2

- Confirm both tokenizer-side sampling mechanisms (or their uniform-sampling replacements) are verified and ready.

- Confirm pre-registration is live on OSF.

Checkpoint 2 gate (end of Day 14) Method A is closed and written up. Method B's sampling infrastructure is verified on both tokenizer families. Pre-registration is timestamped. Do not begin the count-matching pilot until all three are true.

# Week 3 — Method B Pilot and Scale-Up

Day 15 — Aug 2 (Sun)   Count-matching pilot — setup

- Implement the count-matching procedure: record each word's default split, sample an alternative, resample-or-discard on mismatched piece count.

Day 16 — Aug 3 (Mon)   Count-matching pilot — run

- Pilot on a few hundred sentence pairs per language pair.

- Log per-language discard rates from the pilot immediately.

Day 17 — Aug 4 (Tue)   Pilot review

- Check for asymmetric discard rates between languages before scaling — this is the exact failure mode Section 7.3.4 flags.

- Fix any systematic resampling issue found in the pilot.

Day 18 — Aug 5 (Wed)   Scale-up — Urdu–Hindi

- Run the matched-control procedure at full scale for Urdu–Hindi: real vs. count-matched-alternative mean-pooled representations, CKA and cosine similarity.

Day 19 — Aug 6 (Thu)   Scale-up — Serbian

- Run the same procedure for Serbian Cyrillic/Latin, at the depth decided at Checkpoint 1 (Day 9).

Day 20 — Aug 7 (Fri)   Discard-rate audit + buffer

- Finalize per-language discard-rate logs for both pairs; write up any asymmetry as a limitation.

- Buffer day for any overrun from Days 18–19.

Day 21 — Aug 8 (Sat)   Checkpoint 3

- Confirm both language pairs have complete real-vs-matched representation data ready for statistical analysis.

Checkpoint 3 gate (end of Day 21) Matched-control data exists for both pairs at the agreed depth, with discard rates logged. If Urdu–Hindi is behind schedule, the Serbian pair's depth (from the Day 9 decision) is the first thing to trim further — not Urdu–Hindi, which is the primary pair.

# Week 4 — Statistical Analysis

Day 22 — Aug 9 (Sun)   Primary regression

- Run per-layer regressions of representational similarity on real vs. matched-alternative tokenization.

- Apply Benjamini–Hochberg FDR at α = 0.05, one family per (model × outcome variable × language pair).

Day 23 — Aug 10 (Mon)   MRL stretch checkpoint (optional)

- MRL Workshop @ EMNLP 2026 direct-submission deadline falls today — this is a stretch target only.

- If Method A alone is publication-shaped by this point, a short workshop paper is an option; otherwise let this deadline pass without disrupting the main schedule.

Day 24 — Aug 11 (Tue)   Secondary check + robustness

- Run the nested-model fit (subtoken count alone vs. count + fertility differential) via likelihood-ratio test or partial R².

- Remember: this check is explicitly secondary — first cut if time runs short.

Day 25 — Aug 12 (Wed)   Appendix-level robustness

- Run Benjamini–Yekutieli as the arbitrary-dependence robustness check.

- Run the pre-specified TOST equivalence test on any non-significant real-vs-matched comparison.

Day 26 — Aug 13 (Thu)   Cross-metric consistency

- Check whether CKA, cosine, and ANC agree in direction and significance across both pairs; note any metric-dependent conclusion explicitly (this is RQ3).

Day 27 — Aug 14 (Fri)   Results consolidation

- Produce final tables/figures: per-layer degradation curves, discard-rate tables, RQ-by-RQ answer summary.

Day 28 — Aug 15 (Sat)   Checkpoint 4

- Confirm every RQ (1–4) has a data-backed answer, including which of the three pre-drafted write-ups (Section 9) matches the actual outcome.

Checkpoint 4 gate (end of Day 28) All statistics are final. No further analysis choices should be made after seeing which write-up looks most favorable — the three write-up shapes were pre-drafted in Section 9 precisely so this decision isn't made post hoc.

# Week 5 — Writing

Day 29 — Aug 16 (Sun)   Draft — Methods

- Write Methods A and B sections from the pre-registration and analysis logs (not from memory of what you intended to run).

Day 30 — Aug 17 (Mon)   Draft — Results

- Write the Results section against the consolidated tables from Day 27.

Day 31 — Aug 18 (Tue)   Draft — Related Work / Discussion

- Fold Section 6 positioning (Hua et al./mOthello as corroborating evidence, Del & Fishel Urdu-Hindi open question) into the paper's Related Work.

- Write Discussion, tying results back to RQ1–RQ4 and the two-pair generalization question.

Day 32 — Aug 19 (Wed)   Draft — Limitations / Ethics / full pass

- Write Limitations (Section 10 content) and Ethical Considerations verbatim-adapted from the proposal.

- Do a full read-through for consistency between claims and the actual statistical results.

Day 33 — Aug 20 (Thu)   Internal review

- Send draft to Dr. Zeeshan Ali Rana / other readers for feedback.

- Run a plagiarism/similarity check across the full draft, not just the previously flagged sentence.

Day 34 — Aug 21 (Fri)   Revisions

- Incorporate feedback.

- Finalize the code repository, OSF artifacts, and result CSV/JSON releases (Section 13 deliverables) alongside the text.

Day 35 — Aug 22 (Sat)   Checkpoint 5

- Full draft complete and internally reviewed; deliverables (code repo, OSF pre-reg, result artifacts) ready for release.

Checkpoint 5 gate (end of Day 35) Draft is feature-complete. Remaining days are polish and submission logistics, not new analysis or new writing.

# Final Stretch — Submission

Day 36 — Aug 23 (Sun)   Polish

- Copyedit, check all citations against Section 14's reference list, verify figure/table numbering.

Day 37 — Aug 24 (Mon)   Formatting + final checks

- Format to arXiv/venue template.

- Publish the code repo and OSF artifacts publicly; confirm links resolve.

Day 38 — Aug 25 (Tue)   arXiv submission

- Submit to arXiv — the proposal's internal 38-day window closes today.

# Buffer — August 26–30, 2026

Reserved strictly for unresolved technical issues or feedback incorporation, per Section 12. The BlackboxNLP ARR deadline (Aug 28) falls inside this buffer — use it to adapt the arXiv version to the ARR submission format, not to run new analysis.

- Aug 26–27: Adapt the arXiv paper to BlackboxNLP/ARR formatting and length requirements.

- Aug 28: BlackboxNLP ARR submission deadline.

- Aug 29–30: Slack for anything that slipped — genuinely unresolved technical issues only.

# Standing Contingencies (apply at any checkpoint)

- Collaborator-fallback scope reduction: if a checkpoint is missed and no collaborator capacity is available to catch up, cut in this order — secondary robustness checks (Benjamini–Yekutieli, ANC) first, the nested-model secondary check second, Serbian-pair statistical depth third, dashboard deliverable last (it was already optional).

- If the primary-pair (Urdu–Hindi) reproduction fails at Checkpoint 1: promote the Serbian pair to primary-pair statistical depth and report Urdu–Hindi as the secondary, caveated pair.